## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2215-swen-261-04-Team 8
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a customer I want to browse the store so that I can clearly see the store’s inventory of products. | GIVEN the user is browsing the store WHEN there are items present in the inventory THEN the the current items in the inventory are displayed
GIVEN the user is browsing the store WHEN there are no items present in the inventory THEN the store should display that there are no items are currently available
As a customer I want to search the store so that I can find any specific products which I am looking for. | GIVEN a customer searches for a product WHEN a word or phrase is inputted into the search bar THEN relevant items will be shown based on that word or phrase
As a customer I want to be able to add an item to my cart so that I can purchase it in the future. | GIVEN I add an item to my cart WHEN the item is in stock THEN it gets added to the cart.
GIVEN I add an item to my cart WHEN the item is not in stock THEN the item is not added to the cart, and I get an error.
As a customer I want to be able to remove items from my cart because I no longer want to purchase it. | GIVEN I remove an item from my cart WHEN the item is in my cart THEN the item is successfully removed from the cart.
GIVEN I remove an item from my cart WHEN the item is not in my cart THEN I am given an error that the item I am trying to remove is not in my cart.
As a customer I want to login so that I can use the site and see my shopping cart. | GIVEN the user is not logged in WHEN they are on the home page THEN the website should show a login button.
GIVEN the user is not logged in WHEN they click the login button THEN the website should show a login page.
GIVEN the user has entered the correct username and password WHEN they click the submit button THEN the website should log them in.
GIVEN the user has entered an incorrect username and password WHEN they click the submit button THEN the website should prompt them to try again.
GIVEN the user is logged in WHEN they are on the home page THEN the website should show a logout button.
GIVEN the user is logged in WHEN they click the logout button THEN the website should log them out.
As a customer I want the store’s saved inventory data to be read so that the inventory stays up to date between sessions. | GIVEN there are items in the inventory WHEN I go to the store page THEN the available products should be loaded into the page
As a customer I want the store inventory to save so that it stays up to date between sessions. | GIVEN the item that is chosen to update or to add to the inventory is valid WHEN there is a call to update or create that product THEN the expected modifications are made.
GIVEN the item that is chosen to update or to add to the inventory is invalid WHEN there is a call to update or create that product THEN the an error is thrown and the modifications are not made.
As a customer I want to be able to checkout my items so that I can purchase them | GIVEN I proceed to checkout WHEN I have items in my cart THEN I can purchase those items.
GIVEN I proceed to checkout WHEN I have no items in my cart THEN I am not able to proceed further.
Sprint 3 - not implemented, do not test
As an owner I want to login so that I can see and update the store’s inventory. | GIVEN I am not logged in WHEN I am on the home page THEN the website should show a login button.
GIVEN I am not logged in WHEN I click the login button THEN the website should show a login page.
GIVEN I have entered the admin credentials WHEN I click the submit button THEN the website should log me in.
GIVEN I have entered an incorrect username and password WHEN I click the submit button THEN the website should prompt me to try again.
GIVEN I am logged in WHEN I am on the home page THEN the website should show a logout button.
GIVEN I am logged in WHEN I click the logout button THEN the website should log me out.
As an owner I want to be able to message with my clients so that they can communicate with me | GIVEN I am a user without a message sent WHEN I click on the message tab in the menu bar THEN I expect to be taken to the form to fill out a message
GIVEN I am an admin with messages sent from users WHEN I click on the message tab THEN I expect to be taken to a page with the messages sent from all users
GIVEN I am a user on the message form page WHEN I fill out the form and hit send THEN I expect the message to be sent to the admin to view and respond
GIVEN I am an admin with no messages sent from users WHEN I click on the message tab THEN I expect to be taken to a page with a message showing no messages
GIVEN I am a user with a response message from the admin, WHEN I go to the message page THEN I expect to see the response so I can view it.
GIVEN I am an admin with at least one message from a user WHEN I go click on the specific message on the message page I expect to see a pop up with a form for the admin to fill out a response message
GIVEN I am a user with a message sent but not responded to WHEN I go to the message page I expect to see that my message was sent but no response sent.
As an owner I want to post the announcement I wrote to the store so that buyers can be well informed about new information regarding products and services. | GIVEN I am an admin WHEN I go to the announcements page THEN I expect to see a form to fill out new announcements and a list of old announcements.
GIVEN I am an admin WHEN I fill out the announcement form and hit send THEN I expect to have that announcement be shown on all users announcement page.
As a buyer I want to view public admin announcements so that I can be well informed about new information regarding products and services. | GIVEN I am a user WHEN I log in THEN I see an admin announcements button.
GIVEN I am a user WHEN I click the admin announcements button THEN I see an announcements page
As a customer I want to save my shopping cart so that it can persist between sessions. | GIVEN the item that is chosen to update quantity or to add to the cart is valid WHEN there is a call to update or add that product THEN the expected modifications are made.
GIVEN the item that is chosen to update quantity or to add to the cart is valid WHEN there is a call to update or add that product THEN the expected modifications are made.
As a customer I want my saved shopping cart data to be read so that it can persist between sessions. | GIVEN I am logged in to my user account WHEN I open my shopping cart THEN I should see any items from my previous login session