## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Developer I want to submit a request to create a new product (name, price, quantity) so that it is available to in the inventory. | GIVEN I submit a product object WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and return the product object and a status code of 201 (CREATED)
GIVEN I submit a product object WHEN a product with the given name already exists THEN the system should return a status code of 409 (CONFLICT)
As a Developer I want to submit a request to get a single product so that I can access the price and quantity. | GIVEN I submit a request to get a single product WHEN the product exists in the inventory THEN the system should return the item and a status code of 200 (OK)
GIVEN I submit a request to get a single product WHEN the product does not exist in the inventory THEN the system should return a status code of 404 (NOT_FOUND)
As a Developer I want to submit a request to get the entire inventory that I have access to all products and their details. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a Developer I want to submit a request to delete a single product so that it is no longer in the inventory. | GIVEN I submit a request to delete a single product WHEN a product with the given name exists THEN the system should delete it from the inventory and return a status code of 200 (OK)
GIVEN I submit a request to delete a single product WHEN no product with the given name exists THEN the system should return a status code of 404 (NOT_FOUND)
As a Developer I want to submit a request to get the products in the inventory whose name contains the given text so that I have access to only those products. | GIVEN I submit a request to get the products in the inventory whose name contains the given text WHEN products whose name contain the given text exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
GIVEN I submit a request to get the products in the inventory whose name contains the given text WHEN products whose name contain the given text do not exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a Developer I want to submit a request to get the entire inventory so that I have access to all of the products. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK)
GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK)
As a customer I want to browse the store so that I can clearly see the store’s inventory of products. | GIVEN the user is browsing the store WHEN there are items present in the inventory THEN the the current items in the inventory are displayed
GIVEN the user is browsing the store WHEN there are no items present in the inventory THEN the store should display that there are no items are currently available
As a customer I want to search the store so that I can find any specific products which I am looking for. | GIVEN a customer searches for a product WHEN a word or phrase is inputted into the search bar THEN relevant items will be shown based on that word or phrase
As a customer I want to be able to add an item to my cart so that I can purchase it in the future. | GIVEN I add an item to my cart WHEN the item is in stock THEN it gets added to the cart.
GIVEN I add an item to my cart WHEN the item is not in stock THEN the item is not added to the cart, and I get an error.
As a customer I want to be able to remove items from my cart because I no longer want to purchase it. | GIVEN I remove an item from my cart WHEN the item is in my cart THEN the item is successfully removed from the cart.
GIVEN I remove an item from my cart WHEN the item is not in my cart THEN I am given an error that the item I am trying to remove is not in my cart.
As a customer I want to login so that I can use the site and see my shopping cart. | GIVEN the user is not logged in WHEN they are on the home page THEN the website should show a login button.
GIVEN the user is not logged in WHEN they click the login button THEN the website should show a login page.
GIVEN the user has entered the correct username and password WHEN they click the submit button THEN the website should log them in.
GIVEN the user has entered an incorrect username and password WHEN they click the submit button THEN the website should prompt them to try again.
GIVEN the user is logged in WHEN they are on the home page THEN the website should show a logout button.
GIVEN the user is logged in WHEN they click the logout button THEN the website should log them out.
As an owner I want to login so that I can see and update the store’s inventory. | GIVEN I am not logged in WHEN I am on the home page THEN the website should show a login button.
GIVEN I am not logged in WHEN I click the login button THEN the website should show a login page.
GIVEN I have entered the admin credentials WHEN I click the submit button THEN the website should log me in.
GIVEN I have entered an incorrect username and password WHEN I click the submit button THEN the website should prompt me to try again.
GIVEN I am logged in WHEN I am on the home page THEN the website should show a logout button.
GIVEN I am logged in WHEN I click the logout button THEN the website should log me out.